## events
Date | Type | Version | Audience | Purpose | Notes
2022-04-19 | Beta | 0.9 | WaTCH | Initial UI feedback
2022-04-20 | Beta | 0.9 | WaTCH | Initial UI feedback | Move controls to persistent global panel instead of each large popup? Ok to publish data from small sites/buildings?
2022-04-22 | Launch | 1 | Public | Launch
2022-06-01 | Upgrade | 2 | Public | Major upgrade

## current punchlist
Status | Category | Branch | Date Completed | Release | Task | Notes
RELEASED |  |  | 2022-04-19 | 0.9.0 | Implement tab for "upstream" sites.
RELEASED |  |  | 2022-04-19 | 0.9.0 | Map click off-marker restores default plot.
RELEASED |  |  | 2022-04-19 | 0.9.0 | Add large map overlay.
RELEASED |  |  | 2022-04-19 | 0.9.0 | Move date slider to overlay, remove from control panel.
RELEASED |  |  | 2022-05-15 | 1.0.0 | Color map points by alert status - combo of level and trend.
PENDING | Feature - new |  |  |  | Add tab for Ethical considerations of WW testing. | Gordon and Lisa, primarily.
WORKING | Feature improvement | master |  |  | Integrate MU data (live if possible). | Coordinating with David Neff
SHELVED | Feature improvement |  |  |  | Add selector for upstream categories: K-12, Higher-ed, other.
RELEASED |  |  | 2022-04-19 | 0.9.1 | Add State layer to all maps.
NOT STARTED | Feature - new |  |  |  | Add content to info tab.
NOT STARTED | Feature improvement |  |  |  | Add more informative tooltips on maps.
ON HOLD | Feature - new |  |  |  | Add county layers to all maps. | Tried numerous times but doesn't seem to work as advertised.
RELEASED |  |  | 2022-04-20 | 0.9.1 | Move to github.
NOT STARTED | Feature - new |  |  |  | Add sampling regime and responsible lab to control panels.
NOT STARTED | Feature - new |  |  |  | Add popup panel with date-sensitive "talking points" when released?
RELEASED |  |  | 2022-04-30 | 0.9.1 | Deploy from github directly.
NOT STARTED | Feature improvement |  |  |  | Change mean plot to individual line plots per facility?
WORKING | Feature improvement | multipath |  |  | Add capability for multiple pathogens.

## Sheet1
Status | Category
NOT STARTED | Bug fix - minor
WORKING | Bug fix - major
PENDING | Feature improvement
ON HOLD | Feature - new
SHELVED
DONE
RELEASED