## events
Date | Type | Version | Audience | Purpose | Notes
2022-04-19 | Release | 0.9 | WaTCH | Initial UI feedback
2022-04-20 | Feedback | 0.9 | WaTCH | Initial UI feedback | Move controls to persistent global panel instead of each large popup? Ok to publish data from small sites/buildings?
2022-04-22 | Release | 1 | Public | Initial release

## current punchlist
Priority | Status | Date | Release | Task | Notes
1 | DONE | 2022-04-19 | 0.9.0 | Implement tab for "upstream" sites.
1 | DONE | 2022-04-19 | 0.9.0 | Map click off-marker restores default plot.
1 | DONE | 2022-04-19 | 0.9.0 | Add large map overlay.
1 | DONE | 2022-04-19 | 0.9.0 | Move date slider to overlay, remove from control panel.
1 |  |  |  | Color map points by...?? Thinking about deviation from CI of past N samples. Daily? weekly? mean of past X?
2 |  |  |  | Integrate MU data (live if possible). | Coordinating with David Neff
2 |  |  |  | Add selector for upstream categories: K-12, Higher-ed, other.
4 |  |  |  | Add content to info tab.
4 |  |  |  | Add more informative tooltips on maps.
4 | DONE | 2022-04-19 | 0.9.1 | Add State layer to all maps.
4 |  |  |  | Add county layers to all maps.
4 |  |  |  | Move to github.
5 |  |  |  | Add sampling regime and responsible lab to control panels.
7 |  |  |  | Add popup panel with date-sensitive "talking points" when released?